## Matrix (2)
RASCI Matrix | [8 empty] | Roles and Responsibilities
BINA' | [8 empty] | Responsible, Accountable, Consulted, Informed
R | Responsible |  | Assigned to complete the task or deliverable.
A | Accountable |  | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support |  | Provides support during implementation.
C | Consulted |  | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed |  | Must be informed after a decision or action.
Done
Ongoing
Not started
| Activity or Task | Activity # | Status | EC | TI-S | TI-LB | LCPS | Comments/updates
Research component | Publlic opinion survey | Act. 1.1.1 | Done | C | A | C | R | Complete
| Focus Groups discussions | Act. 1.1.2 | Done | C | A | C | R | Complete
| Comparative study: on people-centred recovery in crisis contexts | Act. 1.1.3 | Done | C | A | C | R | Complete
| Report and dissemination of findings | Act. 1.1.4 | Done | C | A | C | R | Complete. Final report sent. Disemmination event held on 14.11.2023
| 6 Analytical pieces on emerging anti-corruption issues relevant to Lebanon | Act. 1.1.6 | Ongoing | I | A | C | C | Two helpdesk answers completed, both in English Arabic. 2 more are being commissioned on public procurement. 4 need to be written until the end of the project.
| Research piece: impact of corruption on groups at risk of discrimination | Act. 3.2.1 | Ongoing | I | A | R | I | TI-LB meeting with the research selected secheduled for Monday 04.12.2023
| Publlic opinion survey: Measuring citizens’ perceptions of the 3RF performance | Act. 3.2.2 | Not started | I | A | C | R | End of the project
| Report on public perceptions and CSO feedback regarding their assessment of the 3RF performance and outcomes | Act. 3.2.3 | Not started | C | A | C | R | End of the project
MFP | Concept and methodology development | Act. 1.1.5 | Done | C | A | R | I | done
| Development of draft/final versions of the sitemap |  | Ongoing | I | A | R | I | Finalization by December 2023
| Development of draft/final versions of the portal |  | Ongoing | I | A | R | I | Finalization by March 2024
| Launching and promoting the portal |  | Not started | I | A | R | I | Launching the portal in April 2024
Cross-sectoral coalition/capacity building | Cross-sectoral coalition to conduct advocacy with respect to the 3RF implementation | Act. 1.2.1 | Ongoing | C | A | R | C | TI-LB Still following up meeting with IOB. We need to see whether this is merged with the next activity after the ROM review.
Communication-based campaigns | Campaings pushing for reforms | Act. 1.2.2 | Ongoing | I | A | R | I | Access to information campaign launch in September 2023 - still ongoing
| Campaign to empower citizens to demand accountability and transparency | Act. 3.1.2 | Not started | I | A | R | I | First quarter of next year 2024
Capacity building | Development and Dissemination of Training Tools | Act. 1.3.3 | Ongoing | C | A | R | I | TOR developed for the potential consultant to develop the training tools - elaborated a plan for capacity building training
| Development of self-paced courses | Act. 2.1.2 | Ongoing | C | A | R | I | Still ongoing - linked to 1.3.3
| Training | Act. 1.3.1 | Ongoing | C | A | R | I | Action plan and vision are being prepared - to start in December 2023
| Training of Trainers | Act. 1.3.2 | Not started | C | A | R | I | Will take place in 2024
Third party financial support | Recruitment of sub grants manager | Act. 2.1.1 | Done | C | A | R | C | Sub-grants manager has been recruited
| Mapping and assessment of CSOs |  | Done | C | A | R | I | done
| Development of relevant documents (methodology, risk register, selection process and criteria...) |  | Done | C | A | C | C | Complete
| Open call for applicactions for the pilot phase |  | Done | C | A | C | I | Complete
| Set up the evaluation committee |  | Done | C | A | C | C | Complete
| Awarding the sub-actions for the pilot phase |  | Done | C | A | R | C | Complete
| Reviewing and updating the relevant documents based on the pilot |  | Done | C | A | R | I | Complete
| Open call for applicactions for the 1st roll-out |  | Done | C | A | R | C | Complete
| Awarding the sub-actions for the 1st roll-out |  | Done | C | A | R | I | Complete
| Open call for applicactions for the 2nd call for proposals |  | Ongoing | C | A | R | C | 2 LOTS: 2nd call for proposals launched online - deadline is January 4, 2024
| Awarding the sub-actions for the 2nd call for proposals |  | Not started | C | A | R | I | starting in Feb 2024
| Open call for applicactions for the 3rd call for proposals |  | Not started | C | A | R | C | Starting in March 2024
| Awarding the sub-actions for the 3rd call for proposals |  | Not started | C | A | R | I | TBC
| Open call for applicactions for the 4th call for proposals |  | Not started | C | A | R | I | Starting in October 2024
| Awarding the sub-actions for the 4th call for proposals |  | Not started | C | A | R | I | TBC
Union of Municipalities dialogues | Post-elections Union of Municipalities dialogues on local accountability, citizen engagement and reforms | Act. 2.2.2 | Not started | C | A | R | I | As elections were postponed will start at the later stage- reevaluated after the ROM review
Roundtable events | Events on anti-corruption strategies and safeguards | Act. 2.3.2 | Not started | C | A | R | I | will start in 2024 - reevaluated after the ROM review
Whistleblowing protection info sessions | LALAC/whistleblowing info sessions | Act. 3.1.1 | Not started | C | A | R | I | Will start in Q1 next year 2024
Info sessions | Good Governance focused information sessions at municipal level | Act. 2.2.1 | Not started | C | A | R | I | will start in 2024
Local integrity system | Local Integrity System Report to assess municipalities work in promoting integrity | Act. 2.3.1 | Not started | C | A | R | I | reevaluated after the ROM review
Government Monitor | Monitoring progress of legislative and policy decisions during 3RF | Act. 2.1.3 | Ongoing | C | A | C | R | 3rd monitor published, 4th will be published soon. LCPS is hiring someone to help with this. To organise a meetign with Makram to better integrate it with MFP
Structured dialogue | Series of issue-based multistakeholder dialogues | Act. 3.3.1 | Ongoing | C | A | R | C | first structured dialogue took place and second one also took place on 16.11.2023
ROM review | ROM review |  | Ongoing | C | A | R | R | Process done - waiting for final report ?
Year 1 review | narrative, logframe, financial review |  | Not started | C | A | R | C
Project Evaluations | Mid-term evaluation |  | Not started | C | A | R | R
Project Evaluations | Final evaluation |  | Not started | C | A | R | R
Insert new rows above this one
R | Responsible |  | Assigned to complete the task or deliverable.
A | Accountable |  | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support |  | Provides support during implementation.
C | Consulted |  | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed |  | Must be informed after a decision or action.
Done
Ongoing
Not started

## Matrix (hidden)
RACI Matrix | [13 empty] | Roles and Responsibilities
BINA' | [13 empty] | Responsible, Accountable, Consulted, Informed
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.
Done
Ongoing
| Activity or Task | Status | EC |  | TI-S |  |  |  | LTA |  |  | LCPS
Research component | Act. 1.1.1: publlic opinion survey Act. 1.1.2: FGDs Act. 1.1.3: comparative study Act. 1.1.4: report and dissemination of findings Act. 1.1.6: analytical pieces Act. 3.2.1: research piece Act. 3.2.2: publlic opinion survey | Ongoing
| Development of concepts/guides/methodologies/questionnaires |  | C | I |  | S | A | C |  | C | R |  | C | R
| Implementing the research |  |  | I |  |  | S | A |  |  | R |  |  | R
| Development of reports/findings |  |  | I |  |  | S | A |  |  | R |  |  | R
| Development of communications visuals |  | I | C |  |  | A | C |  |  | R |  |  | R
MFP | Act. 1.1.5
| recruitment? |  |  | I |  |  | S | C |  |  | R |  |  | C
| Development of draft/final versions of the sitemap |  | A | C |  |  |  | C |  |  | R |  |  | C
| Development of draft/final versions of the portal |  | A | C |  |  |  | C |  |  | R
| Launching and promoting the portal |  | I | C |  |  | S | C |  | A | R |  |  | I
Coalition building and framework | Act. 1.2.1
| Mapping and selection of potential CSOs candidates |  |  | I |  |  |  | C |  |  | R |  |  | C
| Development of draft/final versions of the coalition framework |  |  | C |  |  |  | C |  |  | R |  |  | I
| Establishment of the coalition |  | I | C |  |  |  | S |  | A | R |  |  | I
Communication-based campaigns | Act. 1.2.2
| Development of draft/final versions of the plan |  |  | I |  |  |  | C |  | A | R |  |  | I
| Implementing the campaigns |  |  | I |  |  |  | C |  |  | R |  |  | I
| Development and dissemination of communications visuals/deliverables |  |  | I |  |  | A | C |  | A | R |  |  | I
Capacity building | Act. 1.3.1 training Act. 1.3.2 training of trainers Act. 1.3.3 developmnet of training tools Act. 2.1.2 self-paced course
| Assessment of CSOs |  |  | I |  |  | C | S |  | A | R |  |  | I
| Selection of trainings topics |  |  | I | [5 empty] | A | R |  |  | I
| Recruitment of trainers? |  |  | I |  |  | C | S |  | A | R |  |  | I
| Development of training sessions agenda/program |  |  | I |  |  | S | S |  | A | R |  |  | I
| Delivering the trainings |  |  | I |  |  |  | C |  | A | R |  |  | I
| Development and Dissemination of Training Tools |  |  | C |  |  |  | C |  | A | R |  |  | I
| Development of self-paced courses |  |  | C |  |  |  | C |  | A | R |  |  | I
TPFS | Act. 2.1.1
| Recruitment of consultant |  |  | C |  |  | C | S |  | A | R |  |  | C
| Mapping and assessment of CSOs |  |  | I |  |  |  | S |  | A | R |  |  | I
| Development of relevant documents (methodology, risk register, selection process and criteria...) |  |  | C |  |  | C | S |  | A | R
| Open call for applicactions for the first batch |  |  | C |  |  |  | A |  |  | R |  |  | C
| Set up the selection committee |  |  | R |  |  |  | R |  |  | R |  |  | R
| Awarding the sub-actions |  |  | C |  |  |  | A |  |  | R |  |  | I
| Local integrity system and roudtable events |  |  | C |  |  | S | C |  | A | R
| LALAC/whistleblowing info sessions |  |  | C |  |  | S | C |  | A | R |  |  | I
Structured dialogue | Development of draft/final versions of the concept |  |  | C |  | A | S | C |  |  | R |  |  | R
Insert new rows above this one
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.
Done
Ongoing